Phase 1 Environment Build

Gazebo + PX4 SITL + ROS2, with real physics — Plan & Task Breakdown

Project Black Dragon  ·  Kamalanathan Jude Ernest Paul  ·  7 October 2026  ·  Draft v1

# 1. Objective

Stand up a working simulation environment — Gazebo Harmonic, PX4 SITL and ROS2, running inside WSL2 with GPU passthrough — in which a quadrotor flies under physics-based dynamics and responds to manual commands sent over ROS2. This is Phase 1 of the Black Dragon roadmap and the foundation every later phase (node graph, RL controller, VLM planner, swarm) builds on.

# 2. Scope & exit criterion

In scope: single-drone simulation stack, manual MAVROS control, physics parameters reviewed against a reference drone. Out of scope: any VLM, RL policy, or swarm logic — those are later phases and are deliberately not touched here.

Exit criterion (unchanged from the overall roadmap): the drone responds to a manual MAVROS command sent over ROS2, inside Gazebo, with PX4 SITL in the loop.

# 3. Target stack

| Component | Choice | Notes |
| --- | --- | --- |
| Simulator | Gazebo Harmonic (gz-sim) | GPU-accelerated rendering; confirm WSL2 passthrough before relying on it |
| Middleware | ROS2 — distro TBD (Humble or Jazzy) | Open decision below; drives Ubuntu image choice and ros_gz package availability |
| Flight stack | PX4 SITL via MAVROS | PX4 now also offers a native uXRCE-DDS ROS2 bridge — flagged as a risk, see §6 |
| Airframe | PX4 default x500 quadrotor (SDF) | Starting point; physics parameters revisited in WP-F against a reference drone |
| Host | WSL2 on Windows, GPU passthrough | Single biggest unknown for this phase — validate first, in WP-A |
| GPU | NVIDIA GTX 1650 Ti, 4 GB VRAM | Benchmark actual Gazebo VRAM draw now; it determines headroom for RL training in Phase 4 |

# 4. GPU budget policy

The 4GB card is shared across three consumers over the project's lifetime — Gazebo rendering, RL training, and VLM inference — and that sharing starts being relevant in this phase, not later. Treat the following as hard rules, not defaults to revisit per-task:

- Never run Gazebo rendering and RL training on the GPU at the same time. Training consumes LiDAR and pose only, never pixels, so the renderer brings no benefit during training — run the simulator server-only (gz sim -s -r your_world.sdf). Reserve the GUI for dev/debug and demo recording.

- Strictly sequence the three GPU consumers: Gazebo (dev/debug), RL training, VLM inference. Train with Gazebo headless, fully exit that process, then load the VLM for inference-time evaluation. Treat this as a hard rule, not a preference — a shared 4GB card has zero tolerance for "keep both loaded, it'll probably be fine."

- Quantize the VLM aggressively from the start. 4-bit quantization (bitsandbytes, or a GGUF build via llama.cpp) gets a 2B-class VLM to roughly 1.5–2GB resident — the difference between fitting with headroom and not fitting at all. Don't start from fp16 and discover it doesn't fit; start quantized.

- If rendering must stay on during training (e.g. a future camera-based reward signal), cut cost before accepting the hit: disable shadows, reduce camera sensor resolution, simplify world geometry, lower the physics/render rate. This is a fallback, not a first move — headless is strictly better when available, and the current architecture (RL controller is LiDAR/pose-only) shouldn't need this path at all.

- If headless Gazebo plus the training process is still tight, move training off the 1650 Ti entirely. Rent a cloud GPU (RunPod, Vast.ai, Lambda Labs — an RTX 3090/4090 or A10, cheap by the hour, 24GB+) for the actual training runs and pull trained weights back down to run locally. The 1650 Ti stays for development, debugging, and iteration speed, not long training jobs. This also removes the VRAM ceiling for every phase after this one, not just Phase 1–4.

- Keep the policy network itself small. A goal-conditioned PPO/SAC policy over LiDAR doesn't need much capacity — a small MLP or shallow CNN is plenty. A tiny network leaves more headroom for batch size and replay buffer, which matters more for training stability on a constrained card than model capacity does.

Do rules 1 and 3 unconditionally — they cost nothing and you'd want them regardless. Then run A5's headless benchmark: if the footprint is small (likely), rules 4–5 stay dormant through Phase 1–4. Budget for rule 5 (cloud GPU) by the time Phase 5 attaches the VLM for end-to-end evaluation, since that's where all three consumers get closest to colliding.

# 5. Task breakdown

Seven work packages, roughly sequential. WP-A and WP-B can run in parallel; everything else depends on both.

## WP-A. Host environment (WSL2 + GPU)

| ID | Task | Depends on | Acceptance criteria |
| --- | --- | --- | --- |
| A1 | Confirm WSL2 kernel version and install NVIDIA driver with WSL CUDA/GPU support on the Windows host | — | nvidia-smi runs inside WSL2 and reports the GTX 1650 Ti |
| A2 | Install the WSL2 Ubuntu image matching the chosen ROS2 distro (22.04 for Humble, 24.04 for Jazzy) | A1; ROS2 distro decision | Ubuntu boots in WSL2, apt update succeeds |
| A3 | Verify GPU passthrough for OpenGL/Vulkan (glxinfo, vulkaninfo) from inside WSL2 | A1, A2 | GPU renderer listed is the 1650 Ti, not llvmpipe/software |
| A4 | Configure WSLg (or X11 forwarding) so Gazebo's GUI can display from WSL2 | A3 | A simple GUI app (e.g. glxgears) renders on the Windows desktop |
| A5 | Benchmark VRAM/frame rate for an empty Gazebo world in two modes: GUI (gz sim) and headless server-only (gz sim -s -r) | A4, WP-C installed | Both figures recorded; headless VRAM draw establishes the real training-time baseline, GUI figure establishes the dev/debug baseline |

## WP-B. ROS2 installation & workspace

| ID | Task | Depends on | Acceptance criteria |
| --- | --- | --- | --- |
| B1 | Install the chosen ROS2 distro via apt | A2 | ros2 --version reports the correct distro |
| B2 | Create the colcon workspace layout (src/ tree) following the repo's package conventions | B1 | colcon build succeeds on an empty workspace |
| B3 | Smoke-test the install with the demo talker/listener | B2 | ros2 topic list and talker/listener exchange messages |
| B4 | Decide and document package layout for future nodes (mission_command, vlm_planner, rl_controller, swarm_coord) | B3 | README documents the package map, even if packages are still empty |

## WP-C. Gazebo Harmonic & ROS2 bridge

| ID | Task | Depends on | Acceptance criteria |
| --- | --- | --- | --- |
| C1 | Install Gazebo Harmonic (gz-sim) | A2 | gz sim launches an empty world |
| C2 | Install ros_gz bridge packages matching the ROS2 distro | B1, C1 | ros2 pkg list shows ros_gz_bridge, ros_gz_sim |
| C3 | Bridge /clock and verify ROS2 time sync with the simulation | C2 | ros2 topic hz /clock reports sim-time ticks |
| C4 | Confirm GPU-accelerated rendering in Gazebo itself (not just raw OpenGL) | A3, C1 | Gazebo's own render engine reports GPU backend, not software fallback |

## WP-D. PX4 SITL + Gazebo integration

| ID | Task | Depends on | Acceptance criteria |
| --- | --- | --- | --- |
| D1 | Clone PX4-Autopilot at a release tagged compatible with Gazebo Harmonic | C1 | Version pin recorded in the repo (commit hash or tag) |
| D2 | Build the Gazebo SITL target for the default quadrotor (make px4_sitl gz_x500) | D1, C1 | Build completes with no errors |
| D3 | Launch the x500 model in Gazebo and confirm PX4 SITL connects and can arm | D2, C4 | PX4 shell reports armed; props spin in the Gazebo viewport |
| D4 | Validate telemetry via QGroundControl or the MAVLink console | D3 | QGroundControl shows live attitude/position telemetry from the SITL instance |

## WP-E. MAVROS bridge & manual control

| ID | Task | Depends on | Acceptance criteria |
| --- | --- | --- | --- |
| E1 | Install MAVROS and the MAVLink dialect matching the PX4 version | B1, D1 | ros2 pkg list shows mavros |
| E2 | Configure the MAVROS node to connect to the PX4 SITL UDP endpoint | E1, D3 | MAVROS reports FCU connected |
| E3 | Verify /mavros/state and /mavros/local_position/pose populate correctly | E2 | Topics publish at expected rate with sane values (matches Gazebo pose) |
| E4 | Send an arm / takeoff / velocity command from ROS2 CLI or a test script and confirm the drone responds in Gazebo | E3 | PHASE 1 EXIT CRITERION — commanded motion is visible in the simulation |

## WP-F. Physics fidelity pass

| ID | Task | Depends on | Acceptance criteria |
| --- | --- | --- | --- |
| F1 | Review the default x500 SDF parameters (mass, inertia tensor, motor thrust/torque curves) against a reference drone spec | D2 | Parameter table documented against a named reference airframe |
| F2 | Adjust SDF/airframe parameters where they deviate materially from the reference drone | F1; reference drone decision | Updated SDF checked in; diff from stock x500 documented |
| F3 | Run basic flight-dynamics sanity checks: stable hover, step-response to a velocity command, no divergence | D3/E4 | Hover holds position within a defined tolerance; step response is bounded and settles |
| F4 | Document known physics simplifications (e.g. no wind model yet, approximated rotor drag) | F1–F3 | A short "physics assumptions" note exists in the repo for later reference |
| F5 | Confirm manual control (E4) also works against the headless launch (gz sim -s -r) used for training, not just the GUI launch | E4, A5 | Arm/takeoff/velocity command succeeds identically with no GUI attached |

## WP-G. Documentation & repo scaffolding

| ID | Task | Depends on | Acceptance criteria |
| --- | --- | --- | --- |
| G1 | Write a workspace README covering install/build/run steps end to end | B–E complete | A fresh clone can follow the README to reproduce the running demo |
| G2 | Capture the environment as a reproducible script or devcontainer/Dockerfile | G1 | Setup can be re-run on a clean WSL2 instance without tribal knowledge |
| G3 | Tag a baseline checkpoint in git once E4 passes | E4, G1, G2 | Tagged commit exists marking the Phase 1 exit criterion |

# 6. Risks & mitigations

| Risk | Mitigation |
| --- | --- |
| WSL2 GPU passthrough is flaky for GUI rendering | Validate in WP-A/A3–A5 before any further investment; fall back to headless Gazebo (gz sim -s, no GUI) plus RViz or recorded video if the GUI path fails |
| PX4 / Gazebo / ROS2 version incompatibility | Pin one tested combination (specific PX4 tag, Gazebo Harmonic, one ROS2 distro) and record it in the README rather than tracking "latest" on all three |
| 4 GB VRAM ceiling shared with later RL training (Phase 4) and the VLM (Phase 5) | A5's benchmark is not just a Phase 1 nicety — it tells you how much headroom Gazebo alone leaves for the training phases that come later |
| MAVROS vs. PX4's newer native uXRCE-DDS ROS2 bridge | The original design doc specifies MAVROS; PX4's own docs now lean toward uXRCE-DDS as the ROS2-native path. Worth a deliberate confirm-or-switch decision now rather than discovering a dead end mid-Phase 5 |
| Default x500 physics may not match any real airframe | WP-F treats this explicitly rather than silently shipping stock PX4 defaults as "real physics" |

# 7. Open decisions

These need a call before (or early into) WP-A/WP-D — flagged rather than silently defaulted:

- ROS2 distro: Humble (longer LTS, most mature ros_gz/PX4/MAVROS support) vs. Jazzy (newer, pairs more natively with Gazebo Harmonic).

- Reference real drone for physics parameters in WP-F — a specific commercial airframe spec, or treat the generic PX4 x500 as sufficient for this proof of concept.

- MAVROS vs. PX4's native uXRCE-DDS bridge for the ROS2 connection (see risk above) — confirm MAVROS is still the intended long-term choice.

- Single-drone scaffolding now vs. namespacing topics/nodes for multi-drone from the start, given the swarm layer arrives in Phase 6 of the overall roadmap.

# 8. Definition of done

WP-A through WP-G complete; E4's manual-control exit criterion demonstrated and recorded; a tagged git checkpoint exists; the physics-assumptions note from F4 is checked in. At that point Phase 2 (full node graph with placeholder models) can begin.